## Project Charter
Ulterius Contacts
Group | Name | Role | Email | Office Tel | Cell | Subcom | Time Zone
Executive | Kevin Hallacy | Chief Executive Officer | kevin.hallacy@ulteriustech.com | (316) 440-2537 x204 | (972) 989-2538 |  | CDT
| Alexandros Cavgalar | Chief Technology Officer | alex.cavgalar@ulteriustech.com | (316) 440-2537 x201 | (316)214-7361 |  | CDT
| Nitya N. Singh | Vice President of Quality & Reliability | nitya.singh@ulteriustech.com | (316) 440-2537 x206 | (316) 200-3856 |  | CDT
Core
CSS Corp Contacts
Group | Name | Role | Email | Office Tel | Cell | Subcom | Time Zone
EXECUTIVE | Raj Reddy | Executive Vice President & Chief Delivery Officer, Global | Raj.Reddy@csscorp.com | +1-408 627 2230 | +91-805 625 1111 | - | IST/EST
| David Raj | Executive Vice President & Chief HR Officer, Global | David.Raj@csscorp.com | + 1-650-385-2145 | +91-994015 0888 | - | IST/EST
| Shakheel Navaz | Vice President Enterprise Global Operations | shakheel.navaz@csscorp.com | +1-650 385 2017 | +91 9940173593 | - | IST/EST
| Mahesh M Iyer | Senior Vice President, Account Management | Mahesh.Iyer@csscorp.com | +1 (425) 711-3946 | +1 (425) 711-3946 | - | PST
Point of Contact SERVICE READINESS | Suman Gokul | Director, Service Readiness & Quality | suman.gokul@csscorp.com | +1-650-385-2759 | + 91-9940162030 | Invite to all | IST/EST
Service Assurance OPERATIONS | Samuel Victor | Director, Operations | samuel.victor@csscorp.com | +1 650 385 2008 | +91 9600 072465 | Invite to all | IST/EST
Service Readiness SUPPORT | Jayaraj Murugaiyan | Associate Director - Talent Acquisition | jayaraj.murugaiyan@csscorp.com | '+1(425) 711-2713 | +91 9566045419 | Hiring | IST/EST
| Sankara Narayanan | Program Manager, IT | sankara.narayanan@csscorp.com | +1 650 385 3604 | +91 9500038356 | Invite to all | IST/EST
| Jesu Valiant | Director - Knowledge Engineeering | jesu.valiant@cssscorp.com | +1 650 385 3553 | +91 9600089690 | CRM | IST/EST

## Project Planner_TechSupport+CRM
Location: Chennai, India(AMBIT)
Version: 1.0
CSS Corp - Ulterius, Project Plan (Apr'16)
S.No | Task Description | Primary Owner | Secondary Owner | Status | Start Date | End Date | Comment
I | Phase 1: Proposal & Identification Stage |  |  | In-Progress | 2016-03-22 | 2016-04-15
1 | Project Identification and Implementation | Shakheel | Mahesh | Closed | 2016-03-22 | 2016-04-05
2 | Service Readiness team to send across Project Initiation email | Suman | Mahesh | Closed | 2016-04-05 | 2016-04-05
2.1 | Discuss on Headcount requirement, Location, Type of Services provided, etc. | Mahesh | Suman | Closed | 2016-04-05 | 2016-04-06
2.2 | Share signed NDA form | Sam | Alex | Closed | 2016-04-06 | 2016-04-08 | CSS Corp has sent the reviewed version, awaiting confirmation from Ulterius & Aricent for execution. Sam: Updated Awaiting confirmation from Legal Team. Awaiting confirmation from Kevin for his Feedback. 3-May'16- CSS Corp has shared the signed version, awaiting confirmation from Aricent.
2.3 | Share Contract Agreement (LOI/SOW/MSA) | Mahesh | Ulterius | In-Progress | 2016-04-05 | 2016-04-15 | Work in-progress
2.4 | Initiate Project Creation to Finance Team | Saba | Vishnu | Closed | 2016-04-11 | 2016-04-15
II | Phase 2: Requirement Gathering & Define Project Objectives |  |  | In-Progress | 2016-04-05 | 2016-04-19
3 | Internal Project Kick-off Meeting | Suman | Mahesh | Closed | 2016-04-05 | 2016-04-06
4 | Internal - Recruitment Meeting | Jay | Suman | Closed | 2016-04-06 | 2016-04-08 | Completed
4.1 | Profile Claibration | Jay | Sam | Closed | 2016-04-06 | 2016-04-15 | Finalized Job Description (Owner: Ramya), Discussed on the profile requirement ( Level 2 Profiles) to be recruited, with 4 Years of experience.
4.2 | Sourcing/ Existing pool/ Internal & External resources | Jay | Suman | Closed | 2016-04-06 | 2016-04-08 | Internal reference - Buddy referral program & Weekend drive has been initiated.
4.3 | Screening and Selection Process | Jay | Sam | Closed | 2016-04-06 | 2016-04-08 | Panel and slots has been shared from Operations (Owner: Sam).
4.4 | RRF to be raised | Vishnu | Sam | Closed | 2016-04-06 | 2016-04-08 | JD shared, Interview process and profile requirement discussed.
5 | Internal - Training Meeting | Sam | Ulterius | Closed | 2016-04-06 | 2016-04-15 | Daily recurring meeting has been scheduled.
5.1 | Discuss on the Training Plan (Modules/Content to be covered for Technology and Foundation Training). | Selva | Sam | Closed | 2016-04-06 | 2016-04-15 | Awaiting confirmation from Ulterius/ As per SAM training would be conducted at Aricent (Chennai) at Ulterius end.
5.2 | Share draft training plan | Sam | Ulterius | Closed | 2016-04-06 | 2016-04-15 | 5 Weeks of Ulterius product and Process training & 2 Weeks of Internal training to be conducted at CSS Corp.
5.3 | Identify Trainer, Training room, Training IT requirements ( Software, Hardware, etc.) | Sam | Raghu | Closed | 2016-04-06 | 2016-04-15 | Foundation Training /Refresher training modules to be finalized and discussed.
5.4 | Share Preliminary question for IRD. | Sam | Suman | Closed | 2016-04-06 | 2016-04-15 | On-site Visit and discussion on the training plan has been scheduled.
6 | Internal Meeting - IT INFRA Readiness |  |  | In-Progress | 2016-04-06 | 2016-04-15
6.1 | Seat Allocation ( ODC/Lab Space allocation) | Suman | Saba | Closed | 2016-04-06 | 2016-04-15 | ODC-1 (10th Floor AMBIT), Yet to confirm on the Seat ids. Lab space available, awaiting confirmation on product shipment.
6.2 | Review Contract requirements( Data/Voice) | Saba | Sankar | Closed | 2016-04-06 | 2016-04-15 | CSS Corp Standard ,except Laptop- 8 GB RAM, 500 GB. CSS corp to procure TFN and also setup CRM.
6.3 | Create Group ID | Shankar | Saba | Closed | 2016-04-06 | 2016-04-15 | Awaiting confirmation from Saba.
6.4 | Discuss on Lab Setup - Product shipping process/challenges and ETA From Proforma to delivery. | Saba | Suman | Closed | 2016-04-06 | 2016-04-29 | Suman has shared the shipment process details across to Ulterius. Awaiting for product details and Proforma invoice.
6.5 | Raise RRF / Create PR in SAP | Saba | Sankar | Closed | 2016-04-06 | 2016-04-15 | RRF has been shared, however PR needs to be raised in SAP (Awaiting Ulterius confirmation).
7 | Ulterius EDGE CRM | Dinesh | Jesu | In-Progress | 2016-04-07 | 2016-05-13 | Demo session was conducted and Test Logins was shared, awaiting for feedback.
7.1 | EDGE CRM Demo | Dinesh | Jesu | Closed | 2016-04-07 | 2016-04-08
7.2 | Requirment Gathering - Share feedback/Inputs | Ulterius | Dinesh | In-Progress | 2016-04-19 | 2016-04-29 | Kevin has shared the requirement draft version to Dinesh, 2nd round of discussion was scheduled for discussion.
7.3 | Finalize : CRM Process, Reporting Dashboards | Ulterius | Dinesh | In-Progress | 2016-04-18 | 2016-04-29
7.4 | Finalize : User Interface | Ulterius | Dinesh | Open | 2016-05-02 | 2016-05-13
8 | Project kick-off | Suman | Mahesh | Closed | 2016-04-12 | 2016-04-12
8.1 | Finalize Weekly Recurring Meeting | Suman | Ulterius | Closed | 2016-04-06 | 2016-04-12 | Tuesday 9:00 AM CDT/7:30 PM IST
8.2 | Introduce key Participants | Suman | Mahesh | Closed | 2016-04-12 | 2016-04-12
8.3 | Discuss on Subcommittee meetings for respective Domain | Suman | Mahesh | Closed | 2016-04-12 | 2016-04-12
9 | CSS Corp - Ulterius Recruitment Subcommittee Meeting | Jay | Ulterius | Closed | 2016-04-12 | 2016-04-19 | Discussed during the Weeklly call, The JD was shared through the Portal and the Training material was shared by Alex
10 | CSS Corp - Ulterius Training Subcommittee Meeting | Sam | Ulterius | Pending | TBD | TBD | Alex to schedule a call between Aricent, Ulterius and CSS Corp. Suman is waiting for a confirmation from Gopi. Gopi responded and he is awaiting for NDA sign-off
10.1 | Discuss on training approach/refresher training and training modules. | Sam | Ulterius | In-Progress | 2016-04-11 | 2016-04-22 | Awaitng confirmation from Gopi
10.2 | Ulterius Trainer on-site training requirements ( Timeliness for training, duration of stay and mentoring post launch, etc.) | Sam | Ulterius | In-Progress | 2016-04-11 | 2016-04-22 | Gopi would be the POC and the Trainer from Aricent would be Ravichandar. Alex also would be part of the training.
11 | CSS Corp - Ulterius IT Infra subcommittee Meeting | Sankar | Ulterius | Pending | TBD | TBD
11.1 | Discuss on the Data Connectivity (CRM/External Lab access/VPN requirement, etc.). | Sankar | Ulterius | In-Progress | 2016-04-11 | 2016-04-22 | Awaiting confirmation from Gopi. Connection between CSS Corp, Aricent and Ulterius.
11.2 | Discuss on Voice Connectivity ( TFN/Vanity Number/DID for call routing, etc.). | Sankar | Ulterius | In-Progress | 2016-04-11 | 2016-04-22 | Toll Free Number Procurement is Initiated.
11.3 | Discuss on Lab Setup for Training and Floor readiness, Hardware shipment. | Sankar | Ulterius | In-Progress | 2016-04-11 | 2016-04-22 | Lab Products would be shipped from Ulterius and Aricent. Suman has asked for the details
11.4 | Finalize Lab Readiness, Voice & Data Requirement, review and Sign-off for Implementation | Sankar | Ulterius | In-Progress | 2016-04-11 | 2016-04-22
12 | Create draft Project plan | Flex | Suman | Closed | 2016-04-11 | 2016-04-12
13 | Share finalized project plan with Timeliness for Ulterius review and Sign-off | Suman | Ulterius | Closed | 2016-04-12 | 2016-04-19
III | Phase 3: Project Implementation |  |  | In-Progress | 2016-04-07 | 2016-05-13
14 | Ulterius CRM Implementation | Dinesh | Jesu | Open | 2016-05-16 | 2016-06-17
14.1 | Level-2 Testing | Ulterius | Dinesh | Open | 2016-06-20 | 2016-06-24
15 | Recruitment | Ramya | Jay | In-Progress | 2016-04-07 | 2016-05-20
15.1 | On-boarding Selected Candidates | Jay | Sam | In-Progress | 2016-05-09 | 2016-05-20
16 | INFRA Procure & Deploy | Chandramohan | Sankar | In-Progress | 2016-04-11 | 2016-05-20
16.1 | Training Readiness - All IT requirements for Training (Lab, Data, etc.) | Sankar | Sam | In-Progress | 2016-04-11 | 2016-05-20
16.2 | Training room readiness - system (laptops/desktops), required bandwidth as per the training requirements. | Sankar | Saba | In-Progress | 2016-04-11 | 2016-05-20
16.3 | Training Material - (Hard copy/Soft copy), access to external Lab/Internal lab access. | Sam | Ulterius | In-Progress | 2016-04-11 | 2016-05-20
16.4 | Floor /Bandwidth Requirements - Data Connectivity, Voice connectivity, Lab access, etc. | Sankar | Sam | In-Progress | 2016-04-11 | 2016-05-20
16.5 | Lab Requirements - Rack, Network cabling, raised floor, heat control, DSL , etc. | Saba | Sam | In-Progress | 2016-04-11 | 2016-05-20
IV | Phase 4: Project Execution |  |  | Open | 2016-05-16 | 2016-07-01
17 | Training | CSS Corp | Aricent & Ulterius | Open | 2016-05-16 | 2016-07-01
17.1 | SWAY Training | Ricardo | Sam | Open | 2016-05-16 | 2016-05-20
17.2 | Foundation Training | Selva | Sam | Open | 2016-05-23 | 2016-05-27
17.3 | Ulterius Product and Process Training | Aricent | Sam | Open | 2016-05-30 | 2016-07-01
18 | IT Setup & Lab Setup | Sankar | Anuroop | Open | 2016-06-13 | 2016-06-24
18.1 | Floor Readiness | Enoch | Saba | Open | 2016-06-13 | 2016-06-17
18.2 | Data & Voice Connectivity | Anuroop | Sankar | Open | 2016-06-20 | 2016-06-24
18.3 | Lab Deployment & Connectivity | Anuroop | Saba | Open | 2016-06-13 | 2016-06-24
V | Phase 5: UAT & Go-live |  |  | Open | 2016-06-27 | 2016-07-07
19 | User Acceptance Testing | Sam | Saba | Open | 2016-06-27 | 2016-07-01
20 | CRM User Acceptance Testing | Sam | Dinesh | Open | 2016-06-27 | 2016-07-01
21 | User acceptance testing - share status and feedback | Suman | Ulterius | Open | 2016-07-01 | 2016-07-01
22 | Go-live | CSS Corp | Ulterius | Open | 2016-07-04 | 2016-07-04
22.1 | Go-live Announcement | Suman | Flex | Open | 2016-07-04 | 2016-07-07
VI | Phase 6: Service Delivery |  |  | Open | 2016-07-04 | 2016-07-14
23 | Setup Weekly Operations Call | Sam | Suman | Open | 2016-07-04 | 2016-07-08
24 | Initiate ISO Service Readiness Process | Suman | Aruna | Open | 2016-07-04 | 2016-07-08
25 | PIR - Post-Implementation Review | Suman | Flex | Open | 2016-07-04 | 2016-07-14
25.1 | Feedback form triggered for both Internal Team & Ulterius. | Suman | Flex | Open | 2016-07-04 | 2016-07-07

## Milestone Charter
FTE | Recruitment |  | On-boarding | SWAY training |  | Foundation Training |  | Product Training |  | Go-live
| Start Date | End Date |  | Start Date | End Date | Start Date | End Date | Start Date | End Date
1 -TL & 4 L2 | 2016-04-07 | 2016-05-12 | 2016-05-13 | 2016-05-16 | 2016-05-20 | 2016-05-23 | 2016-05-27 | 2016-05-30 | 2016-07-01 | 2016-07-04

## Recruitment Dashboard
Project | HR |  |  | L1 | [5 empty] | L2 | [7 empty] | Grand Total | Position | Skill | Target Open | Offered | Offer In progress | Remarks
| Reject | Select | HR Total | Awaiting Interview | GTP | Reject | Select | Select as L2 | L1 Total | Awaiting Interview | Drop | Hold | Reject | Offered | To be offered | Select & Hold | L2 Total |  | Senior Network Engineer | R&S | 1 | 1 |  | Muthu Santhosh - DOJ 4th May'16
[19 empty] | Network Specialist | R&S | 1
[19 empty] | Senior Network Engineer | Linux & Networking | 1 | 1 |  | Alamgir Ahmed - DOJ 9thMay
[19 empty] | Senior Network Engineer | Security | 1 | 1 |  | Sony Baby - DOJ 2nd May
[19 empty] | Senior Network Engineer | Wireless | 1 |  | 1 | In-progress
[19 empty] | Grand Total |  | 5 | 3 | 1
Ulterius | 310 | 118 | 428 | 5 | 4 | 83 | 26 | 4 | 118 | 11 | 1 | 2 | 12 | 1 | 2 | 1 | 30 | 576
Domain | S.No | First Name |  |  |  | Last Name |  |  |  | Status |  |  |  | EDOJ
Security | 1 | Sony |  |  |  | Babu |  |  |  | Offered |  |  |  | 2016-05-02
Linux | 2 | Alamgir |  |  |  | Ahmed |  |  |  | Offered |  |  |  | 2016-05-09
R&S | 3 | Muthu |  |  |  | Santhosh |  |  |  | Offered |  |  |  | 2016-05-04

## Training Plan
Training Plan | Owner | Start Date | End Date
Internal training - SWAY | CSS Corp | 2016-05-16 | 2016-05-20
Internal Foundation Training | CSS Corp | 2016-05-23 | 2016-05-27
Ulterius Product & Process Training | Aricent/Ulterius | 2016-05-30 | 2016-07-01
CRM Training | CSS Corp | 2016-07-01 | 2016-07-01

## Action Items
Last updated: | 2016-05-03
CSS Corp-Ulterius: Action Item Tracker
S.No | Field | Action Item description | Owner | Status | Start Date | Due Date | Comment
1 | General | NDA document to be signed and shared for On-site visit | Sam | Closed | 2016-04-12 | 2016-04-15 | CSS Corp has signed and shared the document across to Aricent
2 | General | Share NDA Survial Obligation details to Ulterius Team | Sam | Closed | 2016-04-12 | 2016-04-15
3 | Training | Training Subcommitte meeting to be schedule | Alex | Pending | 2016-04-12 | 2016-04-15 | Awaiting confirmation from Ulterius & Aricent.
4 | CRM | CRM call to be scheduled | Jesu | Closed | 2016-04-12 | 2016-04-15 | Scheduled for 21st Apr'16
5 | IT INFRA | Share IT INFRA readiness questionnaires (Owner: Sankar, Due date: 13th Apr’16). | Sankar | Closed | 2016-04-12 | 2016-04-13 | Awaiting feedback from Gopi
6 | IT INFRA | TFN Procurement | Sankar | In-Progress | 2016-04-12 | 2016-05-15 | Awaiting confirmation on SOW
7 | General | Share Billable forecast from April to July’16 | Mahesh | Closed | 2016-04-12 | 2016-04-15 | Suman to follow-up with Mahesh
8 | Training | Suman to send preliminary questionnaire to Gopi and request for a meeting slot | Suman | Closed | 2016-04-20 | 2016-04-20 | Awaiting feedback from Gopi
9 | General | Sam to share the NDA form to Kevin | Sam | Closed | 2016-04-20 | 2016-04-20 | Awaiting feedback from Kevin
10 | Training | Share On-site Visitor details for Vendor Access Pass | Suman | Closed | 2016-04-20 | 2016-04-27 | Sam to share the details along wih travel dates.
11 | Training | Alex to upload case studies and other learning documents to the FTP | Alex | Closed | 2016-04-20 | 2016-04-27
12 | General | SOW document to be closed | Mahesh | In-Progress | 2016-04-20 | 2016-04-27
13 | Transition | Share itineary details and training schedule to Suman | Alex | In-Progress | 2016-04-26 | 2016-05-03
14 | Training | Testing - Upload test sample case documents to FTP | Alex | Closed | 2016-04-26 | 2016-05-03
15 | Training | Alex to inititate email between Natarajan and Suman on training lab readiness | Alex | In-Progress | 2016-04-26 | 2016-05-03
16 | IT INFRA | Suman to share POC from CSS Corp to work along with Spirent and Aricent for connectivity | Suman | Closed | 2016-04-26 | 2016-05-03 | Gayatri would be the POC from CSS Corp.
Formulas:
Due Date = Table2[[#This Row],[Start Date]]+7

## Weekly Notes
Date: 12th Apr'16
Participants :
· CSS Corp : Mahesh Iyer, Suman Gokul, Samuel Victor, Gayatri, Sankar N, Anuroop K, Jesu Valiant, Dinesh M, Jay & Ramya
· Ulterius : Kevin Hallacy, Alex Cavgalar & Nitya Singh
Discussion Points :
· Transition
o Key Participants from CSS Corp & Ulterius were introduced and their role on this transition was explained
o Overall Project plan and the timeliness were reviewed and agreed that the focus would be on hiring and the timelines may vary depending on when we would onboard candidates for the team
· Recruitment
o Recruitment process has started as per schedule and CSS has shortlisted couple of candidates
o Sam suggested it would be apt to have an understanding about the devices and would like complete the visit to Aricent as soon as possible
o This will enable CSS Corp to start onboarding / offer the right candidates as per the skillset/profile fitment
o Sam also highlighted the point pertaining to the finalization of the 3 party NDA. Sam has shared the details on where it is currently held up and requested support from Ulterius to complete the NDA process. (Links to an Action Item)
· Training
o Suman explained the Internal training approach (SWAY & Foundation Training) and mentioned that the modules would be updated under the Training Plan sheet in the project plan
o Alex updated that he would be traveling to India during the week of 09th May and is available to conduct product training programs. He would be supported by Gopi and Ravi as well
o Alex also shared an overview of the simulators which would be set up for product training (Links to an Action Item)
o Ulterius devices would be sent from Aricent (OMR) to CSS Corp (Ambattur) and some products would be shipped directly from the US (Links to an Action Item)
o Ravi would be the Single point of contact for Training from Ulterius Technologies
· CRM
o Jesu updated the participants that he has completed a demo session with Ulterius and is waiting for feedback (Links to an Action Item)
· IT INFRA Readiness
o Sankar updated on the toll free number procurement and the requirement for the tech support team would be to procure 1 number for now (Links to an Action Item)
o Sankar to send a Questionnaire along with a call flow architecture to Ulterius team to understand the IT set up in detail. (Links to an Action Item)
· Others
o Kevin requested to provide a billable forecast from April to Steady State Operations. Mahesh updated he would share the details (Links to an Action Item)
Action Item
1. Sam to share the survival obligation details to Ulterius (Owner: Sam) – Completed and awaiting response
2. Training subcommittee meeting to be scheduled on Thursday by Ulterius. Product shipment from US and Aricent would also be an agenda (Owner: Alex) – Pending.
3. A follow call on the EDGE CRM to be scheduled during the course of next week (Owner: Jesu) – Pending
4. Sankar to share IT INFRA readiness questionnaires (Owner: Sankar, Due date: 13th Apr’16) Completed and awaiting response
5. Sankar to initiate TFN procurement (Owner: Sankar: 13th Apr’16) – Pending
6. Mahesh to share Billable forecast from April to July’16 (Owner: Mahesh) – Pending
Date: 20th Apr'16
Participants :
· CSS Corp : Suman Gokul, Samuel Victor, Gayatri, Sankar N, Anuroop K, Jay, Ramya & Flex
· Ulterius : Kevin Hallacy, Alex Cavgalar & Nitya Singh
Discussion Points :
· Recruitment
o Current Pipeline: 9 Profiles are lined-up for Level 2 discussion , and 1 Candidate to be on-boarded (Notice Period: 20 days) for Network Security.
o Ramya to share the recruitment Dashboard report, which would be added to Transition plan that would be circulated shortly (Links to an Action Item).
o Suman discussed on the NDA document, and requested ETA to close the process. Alex did confirm he was okay with updated NDA and awaiting for Kevin’s feedback
o Suman to share the name list of Visitors to Aricent for Vendor Access Pass (Links to an Action Item).
o Sam to share the NDA form to Kevin, whilst Kevin to revert with an update (Links to an Action Item).
· Training
o Suman discussed on the Training plan and approach for Ulterius and Alex confirmed that Gopi would be the point of contact and Ravichandar would be the Trainer.
o Suman explained he would reach out to Gopi with the questions both on Training Plan and Lab Devices and seek for his availability for a meeting(Links to an Action Item).
o Alex also confirmed he would sync-up with Gopi as well
o Alex to share the list of products that would be shipped from the US and as well the list of products that would be loaned from Aricent to CSS Corp (Links to Action Item).
· IT INFRA
o As a follow-up on the IT Questionnaire, Alex confirmed that they would be replicating the same connectivity as set up with Aricent (VPN, Remote access, etc.)
o Alex confirmed he would share case studies and other learning material and will have it uploaded to the FTP (Links to an Action Item).
· CRM
o Suman updated he would have Jesu/Dinesh to schedule a separate call to discuss on the EDGE CRM Tool (Links to an Action Item).
· Others
o SOW currently pending under Mahesh (Links to Action Item).
o Kevin requested for billable forecast from April to Steady State operations report. Suman confirmed he would follow-up Mahesh and close the action item (Links to an Action Item).
· Testing
o As a follow-up from yesterday’s call, Suman clarified testing requirement and Alex did confirm to involve Raga from Next Weekly call.
Action Item :
1. Suman to send preliminary questionnaire to Gopi and request for a meeting slot – Completed and awaiting response.
2. Sam to share the NDA form to Kevin (Owner: Sam) – Completed and awaiting response
3. Suman to Share On-site Visitor details for Vendor Access Pass – Pending
4. Alex to upload case studies and other learning documents to the FTP - Pending
5. EDGE CRM discussion call to be scheduled (Owner: Jesu) – Scheduled for today 08:30 PM IST
6. Suman to follow-up with Mahesh on billable forecast for April’15 to July’16 – Completed and Shared with Kevin
7. SOW document to be closed (Owner: Mahesh) – Pending
Date: 26th Apr'16
Participants :
· CSS Corp : Mahesh Iyer, Suman Gokul, Samuel Victor, Jesu Valiant ,Gayatri, Dinesh, Sankar N, Anuroop K, Ramya & Flex
· Ulterius : Kevin Hallacy, Alex Cavgalar & Nitya Singh
Hiring Dashboard :
Position | Skill | Target Open | Offered | Offer In progress
Senior Network Engineer | R&S | 1 |  | 1
Network Specialist | R&S | 1
Senior Network Engineer | Linux & Networking | 1 |  | 1
Senior Network Engineer | Security | 1 | 1
Senior Network Engineer | Wireless | 1
Grand Total |  | 5 | 1 | 2
Action Item :
1. Mahesh to share the SOW document with Kevin ( Owner: Mahesh – Completed and awaiting response).
2. Kevin to share review and sign NDA document (Status: Closed).
3. Alex to share itinerary and Training plan with Suman (Owner: Alex – Pending).
4. Nitya to initiate email on Device shipment from Aricent to CSS Corp (Owner: Nitya – Completed)
5. Alex to initiate email between Natarajan and Suman for Training Lab readiness ( Owner: Alex – Pending)
6. Suman to share the POC from CSS Corp Ambattur to coordinate with SPIRENT Bangalore along with Alex and Aricent team (Owner: Suman – Pending)
7. Alex to upload sample test case and documents to FTP (Owner: Alex – Pending).
Discussion Points:
· Recruitment
o Hiring update: 1 Candidate offered and expected date of Joining - 4th May 2016, 2 selected candidates are yet to be offered for R&S and Linux.
o Alex and Kevin to review the SOW document and to share the signed version by Wednesday (Linked to Action Item – Pending)
o Kevin confirmed he would be able to close the NDA by today (Linked to Action Item – Completed).
· Training
o Alex to share the training plan and itinerary details, he also commented that he and Ravi are running on a tight schedule. Suman to review the dates and share his feedback on the timeliness. Suresh and Ravi’s Team are flexible and would be able to cover if needed.
o Training lab requirement - VBox image, establish connection between Aricent and CSS Corp. Alex to share the details to Suman for establishing connection between Aricent and CSS Corp (Linked to Action Item).
· IT INFRA
o Nitya is currently working along with Aricent team to ship devices (5 Box) to CSS Corp and he also commented the devices are currently shared on temporary basis. Nitya to initiate email and loop CSS Corp for further action (Completed).
o Lab Requirement – Currently 1 Rack allotted and dedicated DSL line to be procured for Ulterius, Alex explained the lab requirements – Vbox Images to be installed in Lab PC/Laptop for soft simulation. He would also updated he would be uploading the drivers and Manual documents into the ftp. Software requirement – Wireshark and PuTTY. POC to be nominated from CSS Corp to work along with him, Aricent Team (Ravi & Nataraj) and Spirent (Linked to action Items)
· Testing
o Raga requested to share sample Test scenarios and Test case documents, Alex updated he would be uploading the documents to the FTP (Linked to Action Item)
Date:3rd May'16
Participants :
· CSS Corp : Suman Gokul, Samuel Victor, Gayatri, Dinesh, Sankar N, Anuroop K, Raga, Ramya & Flex
· Ulterius : Kevin Hallacy, Alex Cavgalar & Nitya Singh
Hiring Dashboard
Position | Skill | Target Open | Offered | Offer In progress
Senior Network Engineer | R&S | 1 | 1
Network Specialist | R&S | 1
Senior Network Engineer | Linux & Networking | 1 | 1
Senior Network Engineer | Security | 1 | 1
Senior Network Engineer | Wireless | 1 |  | 1
Grand Total |  | 5 | 3 | 1
Action items
· Nitya to share Alex travel itinerary (Owner: Nitya, Status – Completed).
· Alex to upload Training documents and lab readiness requirements to the FTP site (Owner: Alex – Pending).
· Suman to schedule a follow-up meeting on Thursday to discuss on Training requirements, CRM and Testing (Status: Completed).
· Awaiting confirmation for On-site visit from Aricent (Owner: Gopi/Ravi).
· Edge CRM – Share feedback on Inventory template and to provide details on Service Contract renewal routines (Owner: Kevin).
· Testing – Alex to upload test case documents to FTP (Owner: Alex – Pending).
Discussion Points
Recruitment
· Ramya updated on the current hiring status – Sony Babu onboarded on 2nd May, whilst Muthu Santhosh and Alamgir Ahmed has accepted the offer and would be onboarding on 4th May and 9th May respectively.
· 2 Candidates have been shortlisted for Wireless and offers to be rolled out. Interview are scheduled for Network specialist and to be closed by this week.
Training
· Confirmation on Signed NDA document, and awaiting confirmation on the On-site Visit dates from Gopi/Ravi.
· Suman requested for the travel itinerary, CSS Corp to arrange Cab from Fortune Palms to CSS Corp AMBIT.
· Alex would be on-site from 10th May to 13th May.
· Alex confirmed he would upload the training documents and Lab setup documents to the FTP (Linked to Action item).
· Nitya confirmed he is currently working on the Product shipment from Aricent to CSS Corp. In the interim, Alex would be carrying the products for Training.
EDGE CRM
· Dinesh has shared the inventory template and awaiting feedback from Kevin and Alex.
IT INFRA
· Call flow – Sankar confirmed once the TFN is procured, he would create a sample call flow and share it with Kevin & Alex.
Testing
Alex to upload the Testing case document in to the ftp and the document would be discussed during the Product Training Meeting scheduled on 5th May.