## Project Charter
Ulterius Contacts
Group | Name | Role | Email | Office Tel | Cell | Subcom | Time Zone
Executive
Core
CSS Corp Contacts
Group | Name | Role | Email | Office Tel | Cell | Subcom | Time Zone
EXECUTIVE | Raj Reddy | Executive Vice President & Chief Delivey Officer, Global | Raj.Reddy@csscorp.com | +1-408 627 2230 | +91-805 625 1111 | - | IST/EST
| David Raj | Executive Vice President & Chief HR Officer, Global | David.Raj@csscorp.com | + 1-650-385-2145 | +91-994015 0888 | - | IST/EST
| Shakheel Navaz | Vice President Enterprise Global Operations | shakheel.navaz@csscorp.com | +1-650 385 2017 | +91 9940173593 | - | IST/EST
| Mahesh M Iyer | Vice President | Mahesh.Iyer@csscorp.com | +1 (425) 711-3946 | +1 (425) 711-3946 | - | PST
Point of Contact SERVICE READINESS | Suman Gokul | Director, Service Readiness & Quality | suman.gokul@csscorp.com | +1-650-385-2759 | + 91-9940162030 | Invite to all | IST/EST
Service Assurance OPERATIONS | Samuel Victor | Director, Operations | samuel.victor@csscorp.com | +1 650 385 2008 | +91 9600 072465 | Invite to all | IST/EST
Service Readiness SUPPORT | Jayaraj Murugaiyan | Associate Director - Talent Acquisition | jayaraj.murugaiyan@csscorp.com | '+1(425) 711-2713 | +91 9566045419 | Hiring | IST/EST
| Sankara Narayanan | Senior Manager, IT | sankara.narayanan@csscorp.com | +1 650 385 3604 | +91 9500038356 | Invite to all | IST/EST
| Jesu Valiant | Director - Knowledge Engineeering | jesu.valiant@cssscorp.com | +1 650 385 3553 | +91 9600089690 | CRM | IST/EST

## Milestone Charter
FTE |  | Recruitment |  | On-boarding | SWAY Training |  | Foundation Training |  | Product & Process(CRM) |  | Go-live
|  | Start Date | End Date |  | Start Date | End Date | Start Date | End Date | Start Date | End Date
TL | 1 | 2016-04-07 | 2016-05-12 | 2016-05-13 | 2016-05-16 | 2016-05-20 | 2016-05-23 | 2016-05-27 | 2016-05-30 | 2016-07-01 | 2016-07-04
L1 | 4 | 2016-04-07 | 2016-05-12
Formulas:
End Date = [SWAY Training]+4

## Project Plan
CSSCORP-Ulterius PROJECT PLAN
LOCATION :Chennai, INDIA
VERSION : draft
SL. NO | CATEGORY | TASK | OWNER | OWNER 2 | START | END | STATUS | COMMENTS
CSS Corp_ Ulterius Project Plan
1 | Contracts | Signing of Statement of Work (SOW) | Client | Mahesh | 2016-04-04 | 2016-04-08 | In-progress |  | OPEN
2 | Contracts | Signing of Master Service Agreement (MSA) | Client | Mahesh | 2016-04-04 | 2016-04-08 | In-progress |  | CLOSED
3 | TRANSITION | Draft version 1.0 of the proposed transition implementation project plan submitted to Ulterius by CSS Corp for approval | Suman | Flex | 2016-04-04 | 2016-04-07 | In-progress
4 | TRANSITION | Begin kick off & recurring project plan meetings between CSS Corp & Ulterius | Suman | Mahesh | 2016-04-07 | 2016-04-07 | Open
5 | RECRUITMENT | Finalize skill set for Recruitment | Client | Samuel | 2016-04-11 | 2016-04-15 | Open
6 | TRAINING | Finalize the Training Curriculum (Internal & Product / Process Related) | Client | Samuel | 2016-04-11 | 2016-04-29 | Open
7 | TRAINING | Creation of Training Content / Review Existing Training Content | Selva | Samuel | 2016-05-02 | 2016-05-13 | Open
8 | IT INFRA | Finalize the Desktop & Software Requirements for the team | Client | Sankara | 2016-04-18 | 2016-05-13 | Open
9 | IT INFRA | Finalize the Data access requirement | Client | Anuroop | 2016-04-18 | 2016-05-13 | Open
10 | IT INFRA | Finalize Telecom / Call Infrastructure Requirement / Call Recording | Client | Sankara | 2016-04-18 | 2016-05-13 | Open
11 | IT INFRA | Finalize Lab Set up / Infrastructure (POWER, LNK, INTERNET & Racks, etc). | Client | Anuroop | 2016-04-11 | 2016-04-15 | Open
12 | IT INFRA | Review Shipment Process in Detail (Review STPI / Customs / WPC Approval Process) | Suman | Client | 2016-04-18 | 2016-05-13 | Open
13 | CRM | CRM Development & Implementation | Jesu | Dinesh | 2016-04-11 | 2016-07-01 | Open
14 | IT INFRA | Setting up of Telecom Infrastructure | Sankara | Saba | 2016-05-16 | 2016-06-17 | Open
15 | IT INFRA | Setting up of Desktop/Laptop's | Sankara | Saba | 2016-06-20 | 2016-06-24 | Open
16 | IT INFRA | Setting up the Lab for Training | Anuroop | Saba | 2016-05-23 | 2016-05-27 | Open
17 | RECRUITMENT | Recruitment ( 1 TL & 4 TAC) | Jay | Samuel | 2016-04-07 | 2016-05-12 | Open
18 | RECRUITMENT | On boarding shortlisted Candidates from the team | Jay | Samuel | 2016-05-13 | 2016-05-13 | Open
19 | TRAINING | SWAY Training | Selva | Samuel | 2016-05-16 | 2016-05-20 | Open
20 | TRAINING | Foundation Training | Selva | Samuel | 2016-05-23 | 2016-05-27 | Open
21 | TRAINING | Ulterius Product & Process Training | Client | Samuel | 2016-05-30 | 2016-07-01 | Open
22 | IT INFRA | Completion of End to End testing | Samuel | Saba | 2016-06-27 | 2016-07-01 | Open
23 | GO-LIVE | Finalize & Roll out Shift Plan | Samuel | Client | 2016-06-27 | 2016-07-01 | Open
24 | GO-LIVE | Go-live | CSS Corp | Ulteriius | 2016-07-04 | 2016-07-04 | Open
25 | GO-LIVE | Set-up a Weekly Operations review Meeting to treview the team performance. | Samuel | Ulteriius | 2016-07-04 | 2016-04-11 | Open
CLOSURE TRANSITION PHASE

## Training Plan
Training Plan | Start Date | End Date
Sway Training | 2016-05-16 | 2016-05-20
Foundation Training | 2016-05-23 | 2016-05-27
Product and Process Training | 2016-05-30 | 2016-07-01
CRM Training | 2016-07-01 | 2016-07-01

## Action Items
CSS Corp-TP-Link : Action Item Tracker
S.No | Field | Action Item description | Owner | Status | Start Date | Due Date | Comment