## SR Dashboard
Customer Service Readiness Plan ¦ Dashboard
Project Status |  | 0%
Completed % |  | 0%
Color Code | Description | Total Items | Per %
76% | Number of very Critical Task | 106 | 100%
51% | Number of Critical Task | 0 | 0%
25% | Number of Task needs attention | 0 | 0%
0% | Number of low priority task | 0 | 0%
- | Up-coming task | 0 | 0%
- | Completed task | 0 | 0%
Total Task |  | 106
Code | Description | Total Items | Per %
TPD | Task pending after the Deadline | 106 | 100%
| > Still in Open status | 106 | 100%
| > In-progress | 0 | 0%
RAS | Task Running as per the schedule | 0 | 0%
| > Still in Open status | 0 | 0%
| > In-progress | 0 | 0%
UTK | Up-coming task | 0 | 0%
CPT | Completed task | 0 | 0%
Total Task |  | 106

## Datasheet (hidden)
[6 empty] | Burn down chart - Datasheet | [5 empty] | Weekly Trend chart - Datasheet
[6 empty] | Note: 1.This data is generated automatically, based on the pivot table. 2. "I column" alone is manual fields, and in "K column" need to drag formula on each complete day. | [5 empty] | Note: 1.This data is generated automatically, based on the pivot table. 2. First Row formula is unique. 3. Week filed need to update manually
Count of End Date | Status
End Date | Completed | In-Progress | Open | (blank) | Grand Total | Day | Planned | Actual | Planned | Actual | Daily Completed | Week | Completed | In-Progress | Open
2015-03-30 |  |  | 1 |  | 1 | 0 |  |  | 94 | 94 | 0 | 2015-03-23 | 0 | 0 | 0 | Row Labels |  | Row Labels
2015-04-01 |  |  | 2 |  | 2 | 1 | 1 | 0 | 93 | 93 | 0 | 2015-03-30 | 0 | 0 | 1 | 2015-03-24 | 1 | 2015-03-30 | 7
2015-04-03 |  |  | 1 |  | 1 | 2 | 2 | 0 | 91 | 91 | 0 | 2015-04-06 | 0 | 0 | 5 | 2015-03-30 | 7 | 2015-04-01 | 9
2015-04-06 |  |  | 2 |  | 2 | 3 | 1 | 0 | 90 | 90 | 0 | 2015-04-13 | 0 | 0 | 16 | 2015-03-31 | 8 | 2015-04-03 | 11
2015-04-08 |  |  | 8 |  | 8 | 4 | 2 | 0 | 88 | 88 | 0 | 2015-04-20 | 0 | 0 | 15 | 2015-04-02 | 10 | 2015-04-06 | 14
2015-04-09 |  |  | 3 |  | 3 | 5 | 8 | 0 | 80 | 80 | 0 | 2015-04-27 | 0 | 0 | 7 | 2015-04-06 | 14 | 2015-04-08 | 16
2015-04-10 |  |  | 4 |  | 4 | 6 | 3 | 0 | 77 | 77 | 0 | 2015-05-04 | 0 | 0 | 1 | 2015-04-07 | 15 | 2015-04-09 | 17
2015-04-13 |  |  | 1 |  | 1 | 7 | 4 | 0 | 73 | 73 | 0 | 2015-05-11 | 0 | 0 | 0 | 2015-04-09 | 17 | 2015-04-10 | 18
2015-04-14 |  |  | 3 |  | 3 | 8 | 1 | 0 | 72 | 72 | 0 | 2015-05-18 | 0 | 0 | 0 | 2015-04-10 | 18 | 2015-04-13 | 21
2015-04-15 |  |  | 2 |  | 2 | 9 | 3 | 0 | 69 | 69 | 0 | 2015-05-25 | 0 | 0 | 0 | 2015-04-13 | 21 | 2015-04-14 | 22
2015-04-16 |  |  | 7 |  | 7 | 10 | 2 | 0 | 67 | 67 | 0 | 2015-06-01 | 0 | 0 | 2 | 2015-04-14 | 22 | 2015-04-15 | 23
2015-04-17 |  |  | 3 |  | 3 | 11 | 7 | 0 | 60 | 60 | 0 | 2015-06-08 | 0 | 0 | 6 | 2015-04-15 | 23 | 2015-04-16 | 24
2015-04-22 |  |  | 7 |  | 7 | 12 | 3 | 0 | 57 | 57 | 0 | 2015-06-15 | 0 | 0 | 2 | 2015-04-16 | 24 | 2015-04-17 | 25
2015-05-01 |  |  | 1 |  | 1 | 13 | 7 | 0 | 50 | 50 | 0 | 2015-06-22 | 0 | 0 | 0 | 2015-04-17 | 25 | 2015-04-22 | 30
2015-05-28 |  |  | 1 |  | 1 | 14 | 1 | 0 | 49 | 49 | 0 | 2015-06-29 | 0 | 0 | 1 | 2015-04-20 | 28 | 2015-05-01 | 39
2015-05-29 |  |  | 1 |  | 1 | 15 | 1 | 0 | 48 | 48 | 0 | 2015-07-06 | 0 | 0 | 0 | 2015-05-15 | 53 | 2015-05-28 | 66
2015-06-02 |  |  | 2 |  | 2 | 16 | 1 | 0 | 47 | 47 | 0 | 2015-07-13 | 0 | 0 | 0 | 2015-05-29 | 67 | 2015-05-29 | 67
2015-06-08 |  |  | 4 |  | 4 | 17 | 2 | 0 | 45 | 45 | 0 | 2015-07-20 | 0 | 0 | 1 | 2015-06-01 | 70 | 2015-06-02 | 71
2015-06-09 |  |  | 2 |  | 2 | 18 | 4 | 0 | 41 | 41 | 0 | 2015-07-27 | 0 | 0 | 10 | 2015-06-03 | 72 | 2015-06-08 | 77
2015-06-25 |  |  | 1 |  | 1 | 19 | 2 | 0 | 39 | 39 | 0 | 2015-08-03 | 0 | 0 | 15 | 2015-06-09 | 78 | 2015-06-09 | 78
2015-07-20 |  |  | 1 |  | 1 | 20 | 1 | 0 | 38 | 38 | 0 | 2015-08-10 | 0 | 0 | 3 | 2015-06-26 | 95 | 2015-06-25 | 94
2015-07-22 |  |  | 3 |  | 3 | 21 | 1 | 0 | 37 | 37 | 0 |  |  |  |  | 2015-07-17 | 116 | 2015-07-20 | 119
2015-07-23 |  |  | 3 |  | 3 | 22 | 3 | 0 | 34 | 34 | 0 |  |  |  |  | 2015-07-21 | 120 | 2015-07-22 | 121
2015-07-24 |  |  | 3 |  | 3 | 23 | 3 | 0 | 31 | 31 | 0 |  |  |  |  | 2015-07-22 | 121 | 2015-07-23 | 122
2015-07-27 |  |  | 1 |  | 1 | 24 | 3 | 0 | 28 | 28 | 0 |  |  |  |  | 2015-07-23 | 122 | 2015-07-24 | 123
2015-07-29 |  |  | 6 |  | 6 | 25 | 1 | 0 | 27 | 27 | 0 |  |  |  |  | 2015-07-24 | 123 | 2015-07-27 | 126
2015-07-30 |  |  | 3 |  | 3 | 26 | 6 | 0 | 21 | 21 | 0 |  |  |  |  | 2015-07-27 | 126 | 2015-07-29 | 128
2015-07-31 |  |  | 4 |  | 4 | 27 | 3 | 0 | 18 | 18 | 0 |  |  |  |  | 2015-07-28 | 127 | 2015-07-30 | 129
2015-08-03 |  |  | 2 |  | 2 | 28 | 4 | 0 | 14 | 14 | 0 |  |  |  |  | 2015-07-29 | 128 | 2015-07-31 | 130
2015-08-04 |  |  | 2 |  | 2 | 29 | 2 | 0 | 12 | 12 | 0 |  |  |  |  | 2015-07-30 | 129 | 2015-08-03 | 133
2015-08-05 |  |  | 1 |  | 1 | 30 | 2 | 0 | 10 | 10 | 0 |  |  |  |  | 2015-07-31 | 130 | 2015-08-04 | 134
2015-08-27 |  |  | 1 |  | 1 | 31 | 1 | 0 | 9 | 9 | 0 |  |  |  |  | 2015-08-03 | 133 | 2015-08-05 | 135
2015-09-03 |  |  | 1 |  | 1 | 32 | 1 | 0 | 8 | 8 | 0 |  |  |  |  | 2015-08-05 | 135 | 2015-08-27 | 157
2015-09-10 |  |  | 1 |  | 1 | 33 | 1 | 0 | 7 | 7 | 0 |  |  |  |  | 2015-08-28 | 158 | 2015-09-03 | 164
2015-10-01 |  |  | 1 |  | 1 | 34 | 1 | 0 | 6 | 6 | 0 |  |  |  |  | 2015-09-04 | 165 | 2015-09-10 | 171
2015-10-08 |  |  | 1 |  | 1 | 35 | 1 | 0 | 5 | 5 | 0 |  |  |  |  | 2015-10-02 | 193 | 2015-10-01 | 192
2015-10-15 |  |  | 1 |  | 1 | 36 | 1 | 0 | 4 | 4 | 0 |  |  |  |  | 2015-10-09 | 200 | 2015-10-08 | 199
2015-11-05 |  |  | 3 |  | 3 | 37 | 1 | 0 | 3 | 3 | 0 |  |  |  |  | 2015-11-06 | 228 | 2015-10-15 | 206
2015-11-10 |  |  | 4 |  | 4 | 38 | 3 | 0 | 0 | 0 | 0 |  |  |  |  | Grand Total | #VALUE! | 2015-11-05 | 227
2015-11-19 |  |  | 3 |  | 3 | 39 | 4 | 0 | 3 | 3 | 0 | [5 empty] | #VALUE! | 2015-11-10 | 232
2015-12-08 |  |  | 1 |  | 1 | 40 | 3 | 0 | 7 | 7 | 0 | [5 empty] | #VALUE! | 2015-11-19 | 241
2016-01-29 |  |  | 2 |  | 2 | 41 | 1 | 0 | 10 | 10 | 0 | [5 empty] | #VALUE! | 2015-12-08 | 260
2016-02-11 |  |  | 2 |  | 2 | 42 | 2 | 0 | 11 | 11 | 0 | [5 empty] | #VALUE! | 2016-01-29 | 312
[7 empty] | 2 | 0 | 13 | 13 | 0 | [5 empty] | #VALUE! | 2016-02-11 | 325
[7 empty] | 0 | 0 | 15 | 15 | 0 | [5 empty] | #VALUE! | Grand Total | #VALUE!
[7 empty] | 0 | 0 | 15 | 15 | 0 | [5 empty] | #VALUE! |  | #VALUE!
[7 empty] | 0 | 0 | 15 | 15 | 0 | [5 empty] | #VALUE! |  | #VALUE!
[7 empty] | 0 | 0 | 15 | 15 | 0 | [5 empty] | #VALUE! |  | #VALUE!
[7 empty] | 0 | 0 | 15 | 15 | 0 | [5 empty] | #VALUE! |  | #VALUE!
[7 empty] | 0 | 0 | 15 | 15 | 0 | [5 empty] | #VALUE! |  | #VALUE!
[7 empty] | 0 | 0 | 15 | 15 | 0 | [5 empty] | #VALUE! |  | #VALUE!
[7 empty] | 0 | 0 | 15 | 15 | 0 | [5 empty] | #VALUE! |  | #VALUE!
[7 empty] | 0 | 0 | 15 | 15 | 0 | [5 empty] | #VALUE! |  | #VALUE!
[7 empty] | 0 | 0 | 15 | 15 | 0 | [5 empty] | #VALUE! |  | #VALUE!
[7 empty] | 0 | 0 | 15 | 15 | 0 | [5 empty] | #VALUE! |  | #VALUE!
[7 empty] | 0 | 0 | 15 | 15 | 0 | [5 empty] | #VALUE! |  | #VALUE!
Formulas:
Week = [Week, row above]+7

## Transition Plan
| Today | 2016-03-01 |  |  | 2016-03-01
Customer Service Readiness Plan | Estimated Go-Live Date: |  |  |  |  | 2015-07-21 |  | Day 120
[16 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111
[16 empty] | 0: 2015-03-23; 7: 2015-03-30; 14: 2015-04-06; 21: 2015-04-13; 28: 2015-04-20; 35: 2015-04-27; 42: 2015-05-04; 49: 2015-05-11; 56: 2015-05-18; 63: 2015-05-25; 70: 2015-06-01; 77: 2015-06-08; 84: 2015-06-15; 91: 2015-06-22; 98: 2015-06-29; 105: 2015-07-06 | 2015-07-13 | [6 empty] | 2015-07-20 | [6 empty] | 2015-07-27 | [6 empty] | 2015-08-03 | [6 empty] | 2015-08-10 | [6 empty] | 2015-08-17 | [6 empty] | 2015-08-24
TASK DESCRIPTION | OWNER | SUPPORT | Start dates | # of Days | Start Date | End Date | Start Day | End Day | Status | Actual Start Date | Actual End Date | #Days Assigned for the task | Code | 1900-02-17 | Task Priority | 0: Week13; 7: Week14; 14: Week15; 21: Week16; 28: Week17; 35: Week18; 42: Week19; 49: Week20; 56: Week21; 63: Week22; 70: Week23; 77: Week24; 84: Week25; 91: Week26; 98: Week27; 105: Week28 | Week29 | [6 empty] | Week30 | [6 empty] | Week31 | [6 empty] | Week32 | [6 empty] | Week33 | [6 empty] | Week34 | [6 empty] | Week35
TASK DESCRIPTION | OWNER | SUPPORT | Start dates | # of Days | Start Date | End Date | Start Day | End Day | Status | Actual Start Date | Actual End Date | #Days Assigned for the task | Code | Code Status | Task Priority | time axis 2015-03-23 to 2015-08-30
Business Opportunity Identification |  |  | 0 | 0 | 2015-03-24 | 2015-04-16 | Day 1 | Day 24 | Open |  |  | 18 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-03-24 to 2015-04-16
CSS submits proposal to Customer | Executive Sponsor |  | 0 | 4 | 2015-03-24 | 2015-03-30 | Day 1 | Day 7 | Open |  |  | 5 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-03-24 to 2015-03-30
CSS and Customer sign SOW/ MSA | Executive Sponsor | Client | 5 | 4 | 2015-03-31 | 2015-04-06 | Day 8 | Day 14 | Open |  |  | 5 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-03-31 to 2015-04-06
Submit Draft version 1.0 of the proposed implementation project plan to Customer | Service Readiness | Client | 10 | 1 | 2015-04-07 | 2015-04-08 | Day 15 | Day 16 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-07 to 2015-04-08
Implementation Plan Sign off | Client |  | 12 | 0 | 2015-04-09 | 2015-04-09 | Day 17 | Day 17 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-09
Toll Gate Review | Service Readiness |  | 17 | 0 | 2015-04-16 | 2015-04-16 | Day 24 | Day 24 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-16
Solution Design |  |  |  |  | 2015-03-30 | 2015-04-17 | Day 7 | Day 25 | Open |  |  | 15 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-03-30 to 2015-04-17
Internal Project Kick-off meeting | Executive Sponsor | Service Readiness | 12 | 0 | 2015-04-09 | 2015-04-09 | Day 17 | Day 17 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-09
Decide on recurring internal meeting schedule with SR Consultants Prepare Information required document (IRD) | Service Readiness |  | 12 | 0 | 2015-04-09 | 2015-04-09 | Day 17 | Day 17 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-09
Project kick- off meeting with Customer - SR Consultants gets introduced to the Client | Service Readiness |  | 13 | 0 | 2015-04-10 | 2015-04-10 | Day 18 | Day 18 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-10
Fix a schedule for all upcoming meetings | Service Readiness |  | 13 | 0 | 2015-04-10 | 2015-04-10 | Day 18 | Day 18 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-10
Share communication matrix | Service Readiness |  | 13 | 0 | 2015-04-10 | 2015-04-10 | Day 18 | Day 18 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-10
Requirement Gathering |  |  | 14 | 2 | 2015-04-13 | 2015-04-15 | Day 21 | Day 23 | Open |  |  | 3 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-13 to 2015-04-15
Analyze Client Requirements |  |  |  |  | 2015-03-30 | 2015-04-16 | Day 7 | Day 24 | Open |  |  | 14 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-03-30 to 2015-04-16
Analyze human resource requirement (skills, knowledge, profile and number of FTEs) | Recruitment Consultant | Service Readiness | 4 | 2 | 2015-03-30 | 2015-04-01 | Day 7 | Day 9 | Open |  |  | 3 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-03-30 to 2015-04-01
Get Client sign-off on JD | Client | Service Readiness | 7 | 1 | 2015-04-02 | 2015-04-03 | Day 10 | Day 11 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-02 to 2015-04-03
Determine Capacity - Seats & Location | Project Management & WFM PMO | Service Readiness | 4 | 2 | 2015-03-30 | 2015-04-01 | Day 7 | Day 9 | Open |  |  | 3 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-03-30 to 2015-04-01
Determine Training requirements -Trainer, Number of days, Classroom, etc | Training Consultant | Service Readiness | 16 | 1 | 2015-04-15 | 2015-04-16 | Day 23 | Day 24 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-15 to 2015-04-16
Determine MIS reporting | MIS Consultant | Service Readiness | 13 | 0 | 2015-04-10 | 2015-04-10 | Day 18 | Day 18 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-10
Determine IT Infrastructure - Bandwidth (E1s, Switches, IP Phones, Servers, Desktops & Software's) | IT Service Readiness | Service Readiness | 17 | 0 | 2015-04-16 | 2015-04-16 | Day 24 | Day 24 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-16
HR Subcommittee Meeting | HR Consultant | Service Readiness | 14 | 0 | 2015-04-13 | 2015-04-13 | Day 21 | Day 21 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-13
Training Subcommittee Meeting | Training Consultant | Service Readiness | 15 | 0 | 2015-04-14 | 2015-04-14 | Day 22 | Day 22 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-14
IT Subcommittee Meeting | IT Service Readiness | Service Readiness | 16 | 0 | 2015-04-15 | 2015-04-15 | Day 23 | Day 23 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-15
Toll Gate Review | Service Readiness |  |  | 0 | 2015-04-17 | 2015-04-17 | Day 25 | Day 25 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-17
Planning & Resourcing |  |  |  |  | 2015-04-06 | 2015-06-15 | Day 14 | Day 78 | Open |  |  | 51 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-06 to 2015-06-15
Devise organizational structure, Roles & Responsibilities | Service Readiness | Recruitment Consultant | 13 | 2 | 2015-04-10 | 2015-04-14 | Day 18 | Day 22 | Open |  |  | 3 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-10 to 2015-04-14
Share Job Description to recruitment | Service Readiness | Client | 9 | 0 | 2015-04-06 | 2015-04-06 | Day 14 | Day 14 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-06
Define team composition (by skill set, knowledge and tenure) | Project Management | Service Readiness | 15 | 0 | 2015-04-14 | 2015-04-14 | Day 22 | Day 22 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-14
CSS - Recruitment Phases | Recruitment Consultant |  |  |  | 2015-05-19 | 2015-06-15 | Day 53 | Day 78 | Open |  |  | 20 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-05-19 to 2015-06-15
Tier I - English & Spanish | Recruitment Consultant |  | 10 | 9 | 2015-04-07 | 2015-04-20 | Day 15 | Day 25 | Open |  |  | 10 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-07 to 2015-04-20
Tier I - English and French | Recruitment Consultant |  | 20 | 19 | 2015-04-21 | 2015-05-18 | Day 28 | Day 39 | Open |  |  | 20 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-21 to 2015-05-18
Tier I - English and German | Recruitment Consultant |  | 40 | 19 | 2015-05-19 | 2015-06-15 | Day 53 | Day 78 | Open |  |  | 20 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-05-19 to 2015-06-15
Finalize Training Requirements | Training Consultant |  |  |  | 2015-06-09 | 2015-06-12 | Day 78 | Day 78 | Open |  |  | 4 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-09 to 2015-06-12
Check on connectivity and whether all Client tools are working in the training room. | Training Consultant |  | 55 | 3 | 2015-06-09 | 2015-06-12 | Day 78 | Day 78 | Open |  |  | 4 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-09 to 2015-06-12
Check all hardware (PC's, Projectors,etc) are all working and available. | Training Consultant |  | 55 | 3 | 2015-06-09 | 2015-06-12 | Day 78 | Day 78 | Open |  |  | 4 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-09 to 2015-06-12
Distribute training schedule to the stakeholders with trainer information. | Training Consultant |  | 55 | 1 | 2015-06-09 | 2015-06-10 | Day 78 | Day 78 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-09 to 2015-06-10
Finalize IT Requirements |  |  |  |  | 2015-04-10 | 2015-04-22 | Day 18 | Day 30 | Open |  |  | 9 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-10 to 2015-04-22
Confirm Seats and release | IT Service Readiness |  | 13 | 4 | 2015-04-10 | 2015-04-16 | Day 18 | Day 24 | Open |  |  | 5 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-10 to 2015-04-16
Check on all hardware requirements (PC's, Headsets, Phones, etc) | IT Service Readiness |  | 17 | 4 | 2015-04-16 | 2015-04-22 | Day 24 | Day 30 | Open |  |  | 5 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-16 to 2015-04-22
Check on VLAN, and the required bandwidth. | IT Service Readiness |  | 17 | 4 | 2015-04-16 | 2015-04-22 | Day 24 | Day 30 | Open |  |  | 5 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-16 to 2015-04-22
Confirm on call routing and path. | IT Service Readiness |  | 17 | 4 | 2015-04-16 | 2015-04-22 | Day 24 | Day 30 | Open |  |  | 5 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-16 to 2015-04-22
Confirm on call recording process, and schedule. | IT Service Readiness |  | 17 | 4 | 2015-04-16 | 2015-04-22 | Day 24 | Day 30 | Open |  |  | 5 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-16 to 2015-04-22
Whitelist to be provided, and prelimanary access to be checked. | IT Service Readiness |  | 17 | 4 | 2015-04-16 | 2015-04-22 | Day 24 | Day 30 | Open |  |  | 5 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-16 to 2015-04-22
Any Special/Additional requirements | IT Service Readiness |  | 17 | 0 | 2015-04-16 | 2015-04-16 | Day 24 | Day 24 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-16
RRF's to be raised | Project Management | IT Service Readiness | 18 | 0 | 2015-04-17 | 2015-04-17 | Day 25 | Day 25 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-17
Implementation (Development, Integration, Training) |  |  |  |  | 2015-04-07 | 2015-09-28 | Day 15 | Day 171 | Open |  |  | 125 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-07 to 2015-08-30
Train the Trainer/Trainer Travel | Client | Training Consultant | 57 |  | 2015-06-11 | 2015-06-22 | Day 78 | Day 78 | Open |  |  | 8 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-11 to 2015-06-22
Training Implementation |  |  |  |  | 2015-06-16 | 2015-09-28 | Day 78 | Day 171 | Open |  |  | 75 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-16 to 2015-08-30
CSS Foundation Training - ENG & SPA | Training Consultant |  | 60 | 4 | 2015-06-16 | 2015-06-22 | Day 78 | Day 78 | Open |  |  | 5 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-16 to 2015-06-22
Product & Process Training - ENG & SPA | Training Consultant |  | 65 | 19 | 2015-06-23 | 2015-07-20 | Day 78 | Day 119 | Open |  |  | 20 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-23 to 2015-07-20
CSS Foundation Training - ENG & FRE | Training Consultant |  | 85 | 4 | 2015-07-21 | 2015-07-27 | Day 120 | Day 126 | Open |  |  | 5 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-07-21 to 2015-07-27
Product & Process Training - ENG & FRE | Training Consultant |  | 90 | 19 | 2015-07-28 | 2015-08-24 | Day 127 | Day 135 | Open |  |  | 20 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-07-28 to 2015-08-24
CSS Foundation Training - ENG & GER | Training Consultant |  | 110 | 4 | 2015-08-25 | 2015-08-31 | Day 135 | Day 157 | Open |  |  | 5 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-08-25 to 2015-08-30
Product & Process Training - ENG & GER | Training Consultant |  | 115 | 19 | 2015-09-01 | 2015-09-28 | Day 158 | Day 171 | Open |  |  | 20 | TPD | TPD: Still in Open after Deadline | 100%
IT Infrastructure Implementation | IT Service Readiness |  |  |  | 2015-04-20 | 2015-06-19 | Day 28 | Day 78 | Open |  |  | 45 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-20 to 2015-06-19
Procure laptops, headphones, Phones, TFN's (Production Seat) | IT Service Readiness |  | 19 | 29 | 2015-04-20 | 2015-05-29 | Day 28 | Day 67 | Open |  |  | 30 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-20 to 2015-05-29
Deploy Phones, headset & computer on production seats | IT Service Readiness |  | 49 | 1 | 2015-06-01 | 2015-06-02 | Day 70 | Day 71 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-01 to 2015-06-02
Install software and tools for Production Machines & supervisor machines | IT Service Readiness |  | 49 | 1 | 2015-06-01 | 2015-06-02 | Day 70 | Day 71 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-01 to 2015-06-02
Create VDN,skill Vector,ADS login, Extn, ACD IDs, NICE mapping &Group Creation in CMS | IT Service Readiness |  | 19 | 9 | 2015-04-20 | 2015-05-01 | Day 28 | Day 39 | Open |  |  | 10 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-20 to 2015-05-01
Share DID to transfer calls to CSS | IT Service Readiness |  | 19 | 2 | 2015-04-20 | 2015-04-22 | Day 28 | Day 30 | Open |  |  | 3 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-20 to 2015-04-22
Provide CRM access & login credentials for agents | Client | Service Readiness | 59 | 4 | 2015-06-15 | 2015-06-19 | Day 78 | Day 78 | Open |  |  | 5 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-15 to 2015-06-19
IT Infrastructure Implementation sign - off | IT Service Readiness | Service Readiness |  |  | 2015-06-19 | 2015-06-19 | Day 78 | Day 78 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-19
QA Process - Defining Quality Assurance process to measure Customer Experience | QA Consultant |  |  |  | 2015-06-16 | 2015-06-24 | Day 78 | Day 78 | Open |  |  | 7 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-16 to 2015-06-24
Create/Share QA Forms & Methodology for different silo | QA Consultant | Client | 60 | 0 | 2015-06-16 | 2015-06-16 | Day 78 | Day 78 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-16
Agree on the methodology for analysis and reporting content and frequency. | QA Consultant | Client | 61 | 2 | 2015-06-17 | 2015-06-19 | Day 78 | Day 78 | Open |  |  | 3 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-17 to 2015-06-19
Upload QA form into QA Portal | QA Consultant |  | 64 | 2 | 2015-06-22 | 2015-06-24 | Day 78 | Day 78 | Open |  |  | 3 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-22 to 2015-06-24
Discuss and Confirm on QA Calibration Process | QA Consultant | Client | 64 | 0 | 2015-06-22 | 2015-06-22 | Day 78 | Day 78 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-22
Client to sign-off QA process | Client | Service Readiness | 64 | 1 | 2015-06-22 | 2015-06-23 | Day 78 | Day 78 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-22 to 2015-06-23
CSAT Survey Process | Operations |  |  |  | 2015-06-12 | 2015-06-25 | Day 78 | Day 94 | Open |  |  | 10 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-12 to 2015-06-25
Client to Share existing CSAT Form, scoring methodology | Client | Operations | 58 | 2 | 2015-06-12 | 2015-06-16 | Day 78 | Day 78 | Open |  |  | 3 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-12 to 2015-06-16
Define CSAT Survey mechanism | Client | Operations | 61 | 2 | 2015-06-17 | 2015-06-19 | Day 78 | Day 78 | Open |  |  | 3 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-17 to 2015-06-19
Agree on methodology for analysis and reporting content and frequency. | Operations | Client | 64 | 1 | 2015-06-22 | 2015-06-23 | Day 78 | Day 78 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-22 to 2015-06-23
Client to Sign-off Csat Process | Client | Service Readiness | 66 | 1 | 2015-06-24 | 2015-06-25 | Day 78 | Day 94 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-24 to 2015-06-25
Workforce Management & MIS | WFM consultant |  |  |  | 2015-06-15 | 2015-06-23 | Day 78 | Day 78 | Open |  |  | 7 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-15 to 2015-06-23
CSS to Provide staffing and scheduling | WFM consultant |  | 59 | 1 | 2015-06-15 | 2015-06-16 | Day 78 | Day 78 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-15 to 2015-06-16
Client to Share the reporting requirement (Format, Frequency & Distro) | Client | WFM consultant | 61 | 2 | 2015-06-17 | 2015-06-19 | Day 78 | Day 78 | Open |  |  | 3 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-17 to 2015-06-19
Share existing reporting formats & template | WFM consultant |  | 59 | 2 | 2015-06-15 | 2015-06-17 | Day 78 | Day 78 | Open |  |  | 3 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-15 to 2015-06-17
WFM & MIS Sign-off | Client | WFM consultant | 62 | 3 | 2015-06-18 | 2015-06-23 | Day 78 | Day 78 | Open |  |  | 4 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-18 to 2015-06-23
Billing Process | MIS Consultant |  |  |  | 2015-04-07 | 2015-04-08 | Day 15 | Day 16 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-07 to 2015-04-08
PO Number | Client |  | 10 | 1 | 2015-04-07 | 2015-04-08 | Day 15 | Day 16 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-07 to 2015-04-08
Billing Method - Hard copy to local address or e-mail | Client |  | 10 | 1 | 2015-04-07 | 2015-04-08 | Day 15 | Day 16 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-07 to 2015-04-08
Billing Cycle | Client |  | 10 | 1 | 2015-04-07 | 2015-04-08 | Day 15 | Day 16 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-07 to 2015-04-08
Address - Address to which invoice to be sent | Client |  | 10 | 1 | 2015-04-07 | 2015-04-08 | Day 15 | Day 16 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-07 to 2015-04-08
E-mail address for billing recipients | Client |  | 10 | 1 | 2015-04-07 | 2015-04-08 | Day 15 | Day 16 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-07 to 2015-04-08
Billing Process, LOI/MSA sent to Finance Consultant | Client |  | 10 | 1 | 2015-04-07 | 2015-04-08 | Day 15 | Day 16 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-04-07 to 2015-04-08
Toll Gate Review | Service Readiness |  |  |  | 2015-06-26 | 2015-06-26 | Day 95 | Day 94 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-26
Go-Live & Nesting |  |  | 135 | 0 | 2015-06-03 | 2015-10-12 | Day 72 | Day 199 | Open |  |  | 94 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-03 to 2015-08-30
User Acceptance Test - Devices/Systems/Application Testing | Operations & IT | Service Readiness |  |  | 2015-06-03 | 2015-06-05 | Day 72 | Day 71 | Open |  |  | 3 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-03 to 2015-06-05
Test and Confirm the functionality of deployed IT Infra structure | Operations & IT | Service Readiness | 51 | 1 | 2015-06-03 | 2015-06-04 | Day 72 | Day 71 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-03 to 2015-06-04
CRM Tool, Call flow,voice quality, access to AVAYA CMS testing, etc | Operations & IT | Service Readiness | 51 | 1 | 2015-06-03 | 2015-06-04 | Day 72 | Day 71 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-03 to 2015-06-04
Check the Application and Tools, required for Client | Operations & IT | Service Readiness | 51 | 1 | 2015-06-03 | 2015-06-04 | Day 72 | Day 71 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-03 to 2015-06-04
Confirm the accessibility ClientURLs & Websites | Operations & IT | Service Readiness | 51 | 1 | 2015-06-03 | 2015-06-04 | Day 72 | Day 71 | Open |  |  | 2 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-03 to 2015-06-04
UAT signoff | Client |  |  |  | 2015-06-05 | 2015-06-05 | Day 72 | Day 71 | Open |  |  | 1 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-06-05
Go-live | All |  |  |  | 2015-09-29 | 2015-10-12 | Day 165 | Day 199 | Open |  |  | 10 | TPD | TPD: Still in Open after Deadline | 100%
Nesting - ENG & SPA | Operations | Service Readiness | 85 | 9 | 2015-07-21 | 2015-08-03 | Day 120 | Day 133 | Open |  |  | 10 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-07-21 to 2015-08-03
Nesting - ENG & FRE | Operations | Service Readiness | 110 | 9 | 2015-08-25 | 2015-09-07 | Day 135 | Day 164 | Open |  |  | 10 | TPD | TPD: Still in Open after Deadline | 100% | bar: 2015-08-25 to 2015-08-30
Nesting - ENG & GER | Operations | Service Readiness | 135 | 9 | 2015-09-29 | 2015-10-12 | Day 165 | Day 199 | Open |  |  | 10 | TPD | TPD: Still in Open after Deadline | 100%
Service Delivery |  |  |  |  | 2015-09-29 | 2016-01-04 | Day 165 | Day 260 | Open |  |  | 70 | TPD | TPD: Still in Open after Deadline | 100%
Establish Service Delivery & Service Assurance communication matrix | Service Readiness |  | 135 | 2 | 2015-09-29 | 2015-10-01 | Day 165 | Day 192 | Open |  |  | 3 | TPD | TPD: Still in Open after Deadline | 100%
Set-up an internal Weekly Operations Meeting to review the teams performance. | Operations | Service Readiness | 135 | 2 | 2015-09-29 | 2015-10-01 | Day 165 | Day 192 | Open |  |  | 3 | TPD | TPD: Still in Open after Deadline | 100%
Set-up a Weekly Call Calibration Meeting to assure our quality monitoring is at goal. | Operations | Service Readiness | 135 | 2 | 2015-09-29 | 2015-10-01 | Day 165 | Day 192 | Open |  |  | 3 | TPD | TPD: Still in Open after Deadline | 100%
Final version of the SIP (Service Implementation Plan) is completed and reviewed. | Operations | Service Readiness | 135 | 22 | 2015-09-29 | 2015-10-29 | Day 165 | Day 206 | Open |  |  | 23 | TPD | TPD: Still in Open after Deadline | 100%
Set-up a Weekly ClientOperations review meeting to review the teams performance. | Operations | Service Readiness | 135 | 2 | 2015-09-29 | 2015-10-01 | Day 165 | Day 192 | Open |  |  | 3 | TPD | TPD: Still in Open after Deadline | 100%
Project handover to Service Delivery | Service Readiness |  | 135 | 60 | 2015-09-29 | 2015-12-22 | Day 165 | Day 260 | Open |  |  | 61 | TPD | TPD: Still in Open after Deadline | 100%
Trigger CSAT survey form to Client | Service Readiness |  | 135 | 60 | 2015-09-29 | 2015-12-22 | Day 165 | Day 260 | Open |  |  | 61 | TPD | TPD: Still in Open after Deadline | 100%
Have a business review with Clientto discuss the first 60 days of the program. | Service Readiness |  | 135 | 69 | 2015-09-29 | 2016-01-04 | Day 165 | Day 260 | Open |  |  | 70 | TPD | TPD: Still in Open after Deadline | 100%
[18 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
`