## Slide 1: Service Readiness Weekly Review
WE22nd Jan 2016
Presented By: Nagalingam R
Reviewed By : Mithran

## Slide 2: Executive Summary – SR Projects Stages
Project | Support | Location | Status
 | English, Korean & Chinese, Japanese, Spanish & Portuguese, French, German | China, India, CR | RFP
 | English and Spanish & English | Utah | Service Delivery
 | English | Utah | In-Progress

## Slide 3: Executive Summary
Key Contributions
Seagate (Dalian & India) Shyamala is not able login to Salesforce, escalated to Sandeep to look in to the issue
Highlights
Airbox (Utah) SL% has improved from 76.81% Nov’15 to 88.45% Dec’15 Abandoned % decreased from 12.35% Nov’15 to 6.15% Last week’s Abandoned % decreased from 5.65% to 3.94%
Help Required
Seagate (Dalian & India) Shyamala is not able login to Salesforce, escalated to Sandeep to look in to the issue
Opportunities
Airbox (Utah) SL% has improved from 76.81% Nov’15 to 88.45% Dec’15 Abandoned % decreased from 12.35% Nov’15 to 6.15% Last week’s Abandoned % decreased from 5.65% to 3.94%

## Slide 4: Last week’s Discussion Point

## Slide 5: Action Items (Airbox TV)
No. | Action Item | Owner | Due By / Closed On | Status
1 | Holiday details to upload it in the IVR | Michael | 24th Dec | Completed
2 | List of Lab equipment been sent to Draper | Sabrina | 11th Nov | Open
3 | MIS Invoicing update | Sunish | 11th Dec | Completed
4 | Outbound calling Auth code for agents | Naga/Sandeep | 11th Dec | Open
5 | Attendance Tracker for the Floor agents | Sabrina/Liz | 30th Nov | Open
6 |  |  |  | 

## Slide 6: Operational Performance
Overall Metrics | 30-Nov | 1-Dec | 2-Dec | 3-Dec | 4-Dec | 5-Dec | 6-Dec | Week 49'15
Calls Offered | 165 | 132 | 105 | 113 | 76 | 97 | 84 | 772
Calls Answered | 141 | 118 | 102 | 93 | 70 | 84 | 69 | 677
Calls Abandoned | 24 | 14 | 3 | 20 | 6 | 13 | 15 | 95
Abandoned % | 14.55% | 10.61% | 2.86% | 17.70% | 7.89% | 13.40% | 17.86% | 12.31%
Avg Speed of Answer | 0:00:38 | 0:00:12 | 0:00:12 | 0:00:40 | 0:00:23 | 0:00:08 | 0:00:25 | 0:00:23
Avg Talk Time | 0:05:21 | 0:05:15 | 0:06:18 | 0:05:06 | 0:05:32 | 0:06:08 | 0:05:32 | 0:05:35
Avg Handle Time | 0:05:28 | 0:05:15 | 0:06:18 | 0:05:08 | 0:05:32 | 0:06:08 | 0:05:32 | 0:05:36
Calls Answerd with in SL | 111 | 111 | 94 | 74 | 63 | 81 | 59 | 593
SL % | 67.27% | 84.09% | 89.52% | 65.49% | 82.89% | 83.51% | 70.24% | 76.81%
Outbound Calls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OB Total Talk Time | 0:00:00 | 0:00:00 | 0:00:00 | 0:00:00 | 0:00:00 | 0:00:00 | 0:00:00 | 0:00:00
OB Avg Talk Time | - | - | - | - | - | - | - | 0:00:00
Longest wait Time | 0:01:11 | - | - | - | - | - | - | 0:01:11