## Sheet1
S.No | Module | Description | Opened | Status | ETA in Hrs | Date | Reviewed | Comment
1 | Project Plan | Auto resize to the Window | 2016-04-13 | Open | 16 |  |  | Fit to window
2 | Project Plan | Column Name - Task Name to be replaced to Task Description | 2016-04-26 | Completed |  | 2016-04-26 | Yes
3 | Project Plan | Comment - Highlight Comment Icon, when a comment is updated | 2016-04-28 | Open | 24 Hrs | 30-May |  | Discussed, on the image change once Comment is updated. Any comments bieng added/updated, please have notification highlghted. " Task No, Commented by "User name on "DD-MMM-YYYY)."
4 | Project Plan | Comment - Auto Save comments |  | Completed |  |  |  | Save comment once updated.
5 | Project Plan | Comment box format | 2016-04-17 | Open | 1 | 24-May |  | S.No not required, Use the User name and time/date format -- Please find the format below. First Name, dd/mmm/yyyy - hh:mm
6 | Project Plan | Comment box window has been set to 598x768 | 2016-04-17 | Open | 1 |  |  | 1237x328, 1164x185 to be set for Text field. - Text Box for 250 Characters, LIFO (Last in first out) Comments to be displayed, Comment Window box to auto align /Screen Fit.
7 | Project Plan | Date selection - Align row 4 & 5 Calendar for date selection | 2016-04-26 | Completed | 2016-04-26 |  | Yes
8 | Project Plan | Duration needs to be calculated in Working days and based on the calendar needs to auto populate the years holiday | 2016-04-17 | Open | NA |  | Yes | Before creating project plan, go to admin->calender to define the holidays and offs. 24th May '16 - Still didn’t work! Please check and revert back. (Refer project under Ulterius technology as the Client).
9 | Project Plan | Multiple selection | 2016-04-26 | Open | NA |  |  | Request will be taken later as involve more complexity. Indent, Outdent, Move-up and Move- down a
10 | Project Plan | Predecessor mapping ( Calculation is incorrect - Need to start from the next day of the mapped task | 2016-04-17 | Open | 16
11 | Project Plan | Project plan saved Message window | 2016-04-17 | Open | 3 |  |  | Format needs to be changed ( proposing green dialogue Top Left corner, right next to Service Readiness Tab ) 2016 - Plan saved window to be lighter version.
12 | Project Plan | Project plan when saved, it showed revert back with the same setting /options selected in the Project plan. | 2016-04-17 | Open | 6 | 24-May |  | The Project plan brings back the Gantt chart, post saving the Plan.
13 | Project Plan | Project plan window size has been set at Static size of 1103x539 | 2016-04-17 | Open | 24 |  |  | Project plan to be set to "Fit to Window"
14 | Project Plan | Status - inprogresss to be changed to In-Progress | 2016-04-26 | Completed | 2016-04-26 | 2016-04-26 | Yes
15 | Project Plan | Task being indent and grouped cannot be moved up or down | 2016-04-13 | Open | NA |  |  | Request will be taken later as involve more complexity
16 | Project Plan | Task description line items to be increased to 100 | 2016-04-26 | Completed | 2016-04-26 | 2016-04-26 | Yes
17 | Project Plan | Task description - To auto align inline with the no# of characters | 2016-04-26 | Open | 16 |  |  | Mouse over the task description shows in Tool Tip, However, we would like to have the complete task description to be displayed
18 | Project Plan | Task Icon - Insert Task Icon - to be interchanged | 2016-04-26 | Completed | 2016-04-26 |  | Yes
19 | Project Plan | Task Icon - Unindent to be replaced with Outdent | 2016-04-26 | Completed | 2016-04-26 |  | Yes
20 | Dashboard | Clock Displays - Dallas (US), Please display all our site | 2016-04-13 | Completed | 1 |  | Yes
21 | Dashboard | Dashboard - Widgets to be able resize and home button to direct back to Dashboard | 2016-04-13 | Completed | NA |  |  | We have already included option for individual dashboard to zoom full screen, we have also placed home button on top to direct back to dashboard
22 | Dashboard | Go-live date - Displays the last date of the project plan. | 2016-04-29 | Open | NA |  |  | the overall end date is the go live date
23 | Dashboard | High-level Plan and upcoming events | 2016-04-29 | Open | 6 |  |  | Unable to save High-level plan from the Project plan
24 | Project Plan | File Attachment - Unable to upload 97-2003 file | 2016-04-17 | Open | 2 Hrs | 24-May |  | Unable to upload 97-2003, 2013, we tried both Excel and Doc. Please do provide multiple selection option/Folder. By defualt it selects image file
25 | Project Plan | File Attachment - Notification "Attachment Icon on the Task description". | 2016-04-17 | Open | 6 | 25-May |  | Any files bieng uploaded, please have notification highlghted. " TaskNo, File has been attahced by "User name on "DD-MMM-YYYY)."
26 | Project Plan | File Attachment - Multiple file upload option | 2016-04-17 | Open | NA |  |  | You have multiple file attachment, click upload button to attach each file.
27 | File Repository | Provide an option to view the file in details/Thumbnail larger, shorter etc. | 2016-04-17 | Open | NA |  |  | Possible only for pdf, text. Doc, excel can be previewd only if the MS office installed else wont be. All other formats cant be previewed.
28 | Project Plan | Start Date and End Date - Format to be changed to dd-MMM-YYYY ( 28-Jun-1984) | 2016-04-17 | Open | 8 Hrs
29 | Project Plan | Start date and End date - Calculation of Working days is incorrect | 2016-04-17 | Open | 8 | 25-May |  | E.g.: If the Start date is on Thursday and the Task duration is 5 days, the Project plan projects - Monday as the end day. Whereas it should be Wednesday.
30 | Project Plan | Project Plan > Provide an Option to "Create a new project" or Select/Open existing Project" | 2016-04-24 | Open |  |  |  | Current state: Creating a project plan, Step 1: Create Cleint Details. Step 2: Create Project Name, Step 3: Map the creator to the project, Step 4: Update the Calendar.
31 | Service Readiness | Project Plan Listing or any other data listing, Please use LIFO method | 2016-04-24 | Open
32 | Communication Matrix | Please provide an option to Add option to the Second field ( To add CSS Corp details below). | 2016-04-24 | Open
33 | User Creation | LIFO Method - Please provide the recent creation first in the list | 2016-04-24 | Open
34 | User Creation | Unable to enter Mobile Name | 2016-04-24 | Open
35 | Communication Matrix | While Exporting the data, it only shows the column header details and not the content | 2016-04-24 | Open
36 | Communication Matrix | Alignment and Word wrap - Refer project Test 3(ETAS) | 2016-04-24 | Open
37 | Org Chart | How do we create a new Org Chart? | 2016-04-24 | Open
38 | Org Chart | When the Org chart has been saved as template, how do we retrive it? | 2016-04-24 | Open
39 | Org Chart | Please provide an option to add dotted(……..) reporting hireachy | 2016-04-24 | Open |  |  |  | We can discuss this in our review this Week.
40 | Project Calendar | Project Calendar saves, however doesn’t reflect on the Project plan | 2016-04-24 | Open